## Project_Schedule
PROJECT SCHEDULE

ACTIVITY	PREDECESSOR	DURATION (Months)
Setup Lab*	-	4
Develop QMS & OHS Plan	-	2
Develop Test Methods	-	1
Staff Recruitment	Setup Lab + Develop QMS & OHS Plan + Develop Test Methods	1
Method Validations	Staff Recruitment	3
SANAS Accreditation	Method Validations	4

TOTAL DURATION		12

PROJECT SCHEDULE NETWORK DIAGRAM

	Setup lab*

	Staff recruitment & training		SANAS accreditaion (Application to assessment date)
Develop QMS / Start		Method Validations, Proficiency testing and internal auditing		Finish

	Develop test methods & SOPs

	1 Month	6 Months	4 Months	Dependent on prederessors
0 Months	6 Months

NB* Lab Setup includes:
Acquisition of premises
Infrastructural development
Furnishing Laboratory
Purchase & commissioning of equipment